# 🟢 PHASE 1 — Specification Freeze (1–3 days)

### 1️⃣ Lock Spec Snapshot

- Freeze TDD v1.1

- Tag it internally (e.g., ArenaRace_TDD_MVP_v1.1_LOCKED)

- No gameplay changes allowed during implementation unless critical

### 2️⃣ Create Implementation Backlog

Split into 4 tracks:

- Smart Contract

- Match Engine Backend

- Queue + Entry Flow

- Infrastructure & DevOps

Do not start coding randomly — start in dependency order below.

# 🔵 PHASE 2 — Smart Contract First (Critical Path)

Everything depends on escrow behavior.

## 3️⃣ Write Escrow Contract

Implement:

- submitEntry()

- entry window logic

- status transitions

- refundMatch() / claimRefund()

- submitResult()

- 38/30/20/12 split

- tie split logic

- reentrancy guard

- pause/unpause

- setResultSigner()

Do NOT connect frontend yet.

## 4️⃣ Unit Test Contract (Hard)

You need tests for:

- 0–3 entries → expire → full refund

- 4 entries → escrow → fee correct (8%)

- submitResult correct payout

- tie split payout

- double submitResult blocked

- expired cannot resolve

- resolved cannot refund

- signer rotation

- pause blocks new entry

- reentrancy attack simulation

Target: 95%+ coverage.

## 5️⃣ Deploy to Testnet

- Deploy contract

- Verify on explorer

- Run 50–100 manual simulated matches

- Test refund expiration manually

Only move forward once contract is stable.

# 🟣 PHASE 3 — Backend Match Engine

Now build deterministic engine.

## 6️⃣ Implement resolveTurn() (Pure Engine First)

No DB. No blockchain. Just logic.

Implement:

- movement

- zone contested logic

- overtake algorithm

- survival logic

- scoring accumulation

- survival cap

- tie-break

Then:

### 7️⃣ Determinism Test

- 1,000 identical simulations → same output

- Randomized stress test (no RNG used in logic)

- Replay full match from action log

Engine must be pure and reproducible before integrating.

# 🟡 PHASE 4 — Entry Flow + Escrow Integration

## 8️⃣ Connect Backend to Contract

Flow:

Queue → Create match → Entry window → Wait for on-chain confirmation → Start match only if Escrowed.

Test cases:

- 4 players pay normally

- 1 player fails to pay

- Entry expires

- Refund triggered

Do NOT allow match to start before Escrowed confirmed.

# 🟠 PHASE 5 — Queue & Timing System

## 9️⃣ Implement Queue Logic

- Redis queue

- FIFO pop 4

- 180s merge

- 240s timeout

- Entry deadline sync with contract

Then:

## 🔟 Implement Turn Timer

- 6000 ms hard window

- receivedAt <= deadline

- no-op default

- late actions ignored

Test:

- Late packet simulation

- Simultaneous action submission

- Player disconnect mid-match

# 🔴 PHASE 6 — Bronze Cushion

## 1️⃣1️⃣ Implement Consecutive 4th Tracker

- Track per user

- Reset on non-4th

- Grant token after 3 consecutive

## 1️⃣2️⃣ Implement Free Entry Funding Flow

- Treasury sends entry when token used

- Contract receives full 4 × entry always

- No special logic in contract

Test:

- Token expiry

- Token stacking prevention

- Token consumed correctly

# 🟤 PHASE 7 — Anti-Collusion (MVP Version)

## 1️⃣3️⃣ Implement:

- Co-occurrence query (15 matches / avg ≤2.2)

- Win-rate flag (≥20 matches, ≥80% over last 50)

- Insert into review_flags

No auto-restrict.

Test:

- Synthetic match data

- Flag creation

- No false positive from small samples

# ⚫ PHASE 8 — Replay & Dispute System

## 1️⃣4️⃣ Build Replay Tool

- Load match_turns

- Re-run resolveTurn

- Compare state

- Compare final score

Test:

- Tamper test (modify one action → mismatch)

- Confirm deterministic reproduction

This is critical for audit confidence.

# 🟢 PHASE 9 — Stress & Simulation

## 1️⃣5️⃣ Run 1,000 Match Simulation

- Automated matches

- Random legal actions

- Verify:

  - Always 1–4 placement

  - Payout sum = 92%

  - Survival cap applied

  - Overtake cap enforced

## 1️⃣6️⃣ Concurrency Stress

- 4 matches simultaneously

- 8 matches

- RPC latency simulation

- Entry race condition test

# 🟢 PHASE 10 — Security Hardening

## 1️⃣7️⃣ Key Management

- Move signer key to HSM/secret manager

- Multisig configured

- Rotation dry run on testnet

## 1️⃣8️⃣ Red-Team Pass

Simulate:

- Double entry attack

- Reentrancy attempt

- Signature replay

- Expired match forced resolution

- Entry window race

- Late submitResult

Fix anything discovered.

# 🟢 PHASE 11 — Audit Prep

## 1️⃣9️⃣ Contract Audit

Provide:

- Full TDD

- Test coverage

- Edge-case list

- State transition diagram

Fix findings.

# 🟢 PHASE 12 — Production Readiness Gate

Before mainnet:

Checklist must be TRUE:

- 100+ testnet matches

- Entry expiration verified

- Refund verified

- Tie payout verified

- Pause tested

- Signer rotation tested

- Replay verified

- 1,000 sim matches clean

- No unresolved critical bug

Only then deploy to mainnet.

# 🟢 PHASE 13 — Mainnet Launch

## 2️⃣0️⃣ Deploy Contract

- Verify

- Configure multisig

- Set signer

- Run 1 live internal match

## 2️⃣1️⃣ Soft Launch

- Invite-only first

- Low volume

- Monitor RPC & payout success

## 2️⃣2️⃣ Open Public Phase 1a

Bronze only.
2 queues.
Monitor DAU + queue time.

# 🧠 Realistic Timeline (3–5 Engineers)

| Phase | Duration |
| --- | --- |
| Contract + tests | 2–3 weeks |
| Engine + determinism | 2–3 weeks |
| Integration + queue | 2 weeks |
| Replay + stress + polish | 2 weeks |
| Audit + fixes | 2–4 weeks |

Total realistic MVP: 10–14 weeks.

# 🎯 Final Execution Rule

Do NOT:

- Add ability draft

- Add multiple boards

- Add Silver division

- Add diminishing zone

- Add auto-restrict

- Add fancy UI features

Until MVP stable for 30+ days.